## Summary
STATUS | COUNT
For Verification | 34
For Review | 10
Doubts/Clarification | 10
In Progress | 4
Not Started | 80
DONE / STREAMLINED | 33
OBSOLETE | 4
Total | 175
Legends:
For Verification - Script completed by Product QA, and need to be executed and verified if working
For Review - Script Completed without any conflicts waiting for approval to commit
Doubts/ Clarification - Some conflicts occurred while running.
In Progress - Working on the Script.
Not Started - Work not started.
DONE - Completed Script with PASSED Status. Test Scripts was merged / streamlined to other test script

## Air Fare
Sub Folder | Test Case | Status | Scripter | Country | Reviewer | Client | Traveller | Tags | Comments
Fare Details | [NB SG] Verify That High, Low And Charged Fare Are Written In The PNR | DONE | Yatheesh | SG | Jayson | APAC SYN CORP ¦ AUTOMATION SG - US273 | BEAR, TWOSEVENTHREE | US273
| [AB SG] Verify That High, Low And Charged Fare Are Written In The PNR When Flights Are Retained | DONE | Yatheesh | SG | Jayson |  | BEAR, TWOSEVENTHREE | US273
| [AB SG] Verify That High, Low And Charged Fare Are Written In The PNR When Flights Are Cancelled And Rebooked | DONE | Yatheesh | SG | Jayson
| [NB HK] Verify That High, Low And Charged Fare Are Written In The PNR | DONE | Yatheesh | HK | Jayson | APAC SYN CORP ¦ AUTOMATION HK - US273 | BEAR, HKTWOSEVENTHREE | US273
| [AB HK] Verify That High, Low And Charged Fare Are Written In The PNR When Flights Are Retained | DONE | Yatheesh | HK | Jayson
| [NB IN] Verify That High, Low And Charged Fare Are Written In The PNR | DONE | Yatheesh | IN | Jayson | APAC SYN CORP ¦ AUTOMATION IN - US273 | BEAR, INTWOSEVENTHREE | US273
| [AB IN] Verify That High, Low And Charged Fare Are Written In The PNR When Flights Are Retained | DONE | Yatheesh | IN | Jayson
| [NB SG] Verify That Air Miscellaneous Information Are Pre-populated And Remarks Are Written For Single Fare | For Review | Harsha | SG | Jayson | APAC SYN CORP ¦ AUTOMATION SG - US285 | BEAR, SGTWOEIGHTFIVE | US285 , US404 , US308
| [AB SG] Verify That Air Miscellaneous Information Are Pre-populated And Remarks Are Written For Multiple Fare | For Review | Harsha | SG | Jayson
| [NB HK] Verify That Air Miscellaneous Information Are Pre-populated And Remarks Are Written For Multiple Fare | For Review | Harsha | HK | Jayson | APAC SYN CORP ¦ AUTOMATION HK - US285 | BEAR, HKTWOEIGHTFIVE | US285 , US404 , US308
| [AB HK] Verify That Air Miscellaneous Information Are Pre-populated And Remarks Are Written For Multiple Fare | DONE | Harsha | HK | Jayson
| [NB IN] Verify That Air Miscellaneous Information Are Pre-populated And Remarks Are Written For Multiple Fare | DONE | Harsha | IN | Jayson | APAC SYN CORP ¦ AUTOMATION IN - US285 | BEAR , INTWOEIGHTFIVE | US285 , US404 , US308
| [AB IN] Verify That Air Miscellaneous Information Are Pre-populated And Remarks Are Written For Multiple Fare | For Review | Harsha | IN | Jayson
| [NB SG] Verify That Correct Routing Itinerary Remarks And Turnaround Accounting Remarks Are Written For Single Fare | DONE | Yatheesh | SG | Jayson | APAC SYN CORP ¦ AUTOMATION SG - US274 | BEAR, TWOSEVENFOUR | US274
| [AB SG] Verify That Correct Routing Itinerary Remarks And Turnaround Accounting Remarks Are Written When Flights/Fares were retained For Single Fare | DONE | Yatheesh | SG | Jayson
| [NB IN] Verify That Correct Routing Itinerary Remarks And Turnaround Accounting Remarks Are Written For Multiple Fares | Not Started |  | IN | Jayson | APAC SYN CORP ¦ AUTOMATION IN - US274 | BEAR , INTWOSEVENFOUR | US274
| [AB IN] Verify That Correct Routing Itinerary Remarks And Turnaround Accounting Remarks Are Written When Flights/Fares were retained For Multiple Fares | Not Started |  | IN | Jayson
| [NB HK] Verify That Correct Routing Itinerary Remarks And Turnaround Accounting Remarks Are Written For Multiple Fares | DONE | Harsha | HK | Jayson | APAC SYN CORP ¦ AUTOMATION HK - US274 | BEAR , HKTWOSVENFOUR | US274
| [AB HK] Verify That Correct Routing Itinerary Remarks And Turnaround Accounting Remarks Are Written When Flights Were Cancelled/Rebooked For Multiple Fares | DONE | Harsha | HK | Jayson
| [NB HK] Verify That Correct MIS Codes Are Listed, Pre-selected and Written To Back Office Remark when HF = CF > LF For Single Fare | DONE | Harsha | HK | Jayson | APAC SYN CORP ¦ AUTOMATION HK - US272 | BEAR , HKTWOSVENTWO | US272
| [AB HK] Verify That Correct MIS Codes Are Listed, Pre-selected and Written To Back Office Remark For Multiple Fares | DONE | Harsha | HK | Jayson
| [NB SG] Verify That Correct MIS Codes Are Listed, Pre-selected and Written to Back Office Remark | Not Started |  | SG | Jayson | APAC SYN CORP ¦ AUTOMATION SG - US272 | BEAR , SGTWOSVENTWO | US272
| [AB SG] Verify That Correct MIS Codes Are Listed, Pre-selected and Written To Back Office Remark For Multiple Fares | Not Started |  | SG | Jayson
| [NB IN] Verify That Correct MIS Codes Are Listed, Pre-selected and Written to Back Office Remark for Multiple Fare | In Progress | Harsha | IN | Jayson | APAC SYN CORP ¦ AUTOMATION IN - US272 | BEAR , INTWOSVENTWO | US272
| [AB IN] Verify That Correct MIS Codes Are Listed, Pre-selected and Written To Back Office Remark For Multiple Fares | In Progress | Harsha | IN | Jayson
| [NB HK] Verify That Air Fare Panel Fields Behave Correctly | In Progress | Gajendra | HK | Jayson | APAC SYN CORP ¦ US774 HK | BEAR , HKSEVENSEVENFOUR | US774
| [NB IN] Verify That Air Fare Panel Fields Behave Correctly | Not Started |  | IN | Jayson | APAC SYN CORP ¦ US774 IN | BEAR , INSEVENSEVENFOUR | US774
| [AB IN] Verify That Air Fare Panel Fields Behave Correctly | Not Started |  | IN | Jayson
| [NB SG] Verify That Air Fare Panel Fields Behave Correctly | Not Started |  | SG | Jayson | APAC SYN CORP ¦ US774 SG | BEAR , SGSEVENSEVENFOUR | US774
| [AB SG] Verify That Air Fare Panel Fields Behave Correctly | Not Started |  | SG | Jayson
| [NB SG] Verify That Nett Fare Are Written In The PNR | Not Started |  | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US273
| [AB SG] Verify That Nett Fare Are Written In The PNR | Not Started |  | SG | Jayson
| [NB IN] Verify That High, Low, And Charged Fare Are Written In The PNR When FXA And FXL Responses Have Different Formats | Not Started |  | IN | Jayson | APAC SYN CORP ¦ AUTOMATION IN - US273 | BEAR , INTWOSEVENTHREE | DE81 , DE80
| [AB IN] Verify That High, Low, And Charged Fare Are Written In The PNR When FXA And FXL Responses Have Different Formats | Not Started |  | IN | Jayson
Fees | [NB SG] Verify That Updated Transaction Fee Amount Is Written In Itinerary And Accounting Remarks When Original Fee Is Overwritten And FOP Are AX CTCL And VI [Amount] |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG | BEAR , ARLENE | US266 , US854
| [AB SG] Verify That Transaction Fee Amount Is Written In Itinerary And Accounting Remarks When FOP Are DC TP And TMP [Amount] |  | Len | SG | Jayson
| [NB HK] Verify FOP Lines in Accouting Remarks for each Fare Quote tab are NOT Written when Transaction fee is Zero and FOP Are Cash CA And AX [Amount] |  | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US266
| [AB HK] Verify FOP Lines in Accouting Remarks for each Fare Quote tab are NOT Written when Transaction fee is Zero and FOP Are TMP DC And TP [Amount] |  | Len | HK | Jayson
| [NB SG] Verify That Correct Transaction Fee Is Written In Itinerary And Accounting Remarks When FOP Is Citi TMP Card And Single Segment [Percentage] |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 2 | BEAR , RING | US266
| [AB SG] Verify That Correct Transaction Fee Is Written In Itinerary And Accounting Remarks When FOP Is VI And Single Segment [Percentage] |  | Len | SG | Jayson
| [NB IN] Verify That Updated Transaction Fee Amount Is Written In Itinerary And Accounting Remarks When Original Fee Is Overwritten And FOP Is DC [Percentage] |  | Len | IN | Jayson | APAC SYN CORP ¦ APAC SYN IN | BEAR , INDI | US266
| [AB IN] Verify That Updated Transaction Fee Amount Is Written In Itinerary And Accounting Remarks When Original Fee Is Overwritten And FOP Is CA [Percentage] |  | Len | IN | Jayson
| [NB SG] Verify That Offine Range Fee Amount Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP Cash Is Used |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US521
| [AB SG] Verify That Offine Range Fee Amount Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When CC VI Is Used |  | Len | SG | Jayson
| [NB SG] Verify That Offine Range Fee Percentage With Cap Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP CC AX Is Used |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 4 | BEAR , NAH | US521
| [AB SG] Verify That Offine Range Fee Percentage With Cap Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP CC DC Is Used |  | Len | SG | Jayson
| [NB IN] Verify That Offine Range Fee Amount Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP TMP UATP (VI) Is Used |  | Len | IN | Jayson | APAC SYN CORP ¦ APAC SYN IN 3 | BEAR , NIYAK | US521
| [AB IN] Verify That Offine Range Fee Amount Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP CC DC Is Used |  | Len | IN | Jayson
| [NB IN] Verify That Offine Range Fee Percentage Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP CC DC Is Used |  | Len | IN | Jayson | APAC SYN CORP ¦ APAC SYN IN 4 | BEAR , ISTA | US521
| [AB IN] Verify That Offine Range Fee Percentage Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP Cash Is Used |  | Len | IN | Jayson
| [NB HK] Verify That Offine Range Fee Amount Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP CC DC Is Used |  | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK 3 | BEAR , PABLO | US521
| [AB HK] Verify That Offine Range Fee Amount Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP TMP CC CA Is Used |  | Len | HK | Jayson
| [NB HK] Verify That Offine Range Fee Percentage Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP CC TP Is Used |  | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN IN 4 | BEAR , ISTA | US521
| [AB HK] Verify That Offine Range Fee Percentage Are Retrieved When Base Fare, Equivalent Fare, and Nett Fare Are Used When FOP Invoice Is Used |  | Len | HK | Jayson
| [NB SG] Verify That Transaction Fee, Accounting and Itinerary Remarks Written Are Correct When Nett Fare Is Present And FOP Cash Is Used |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US521
| [AB SG] Verify That Transaction Fee, Accounting and Itinerary Remarks Written Are Correct When Nett Fare Is Present And FOP CC VI Is Used |  | Len | SG | Jayson
| [NB HK] Verify That Transaction Fee, Accounting and Itinerary Remarks Written Are Correct When Nett Fare Is Present And FOP CC DC Is Used |  | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK 3 | BEAR , PABLO | US521
| [AB HK] Verify That Transaction Fee, Accounting and Itinerary Remarks Written Are Correct When Nett Fare Is Present And FOP CC CA Is Used |  | Len | HK | Jayson
| [NB SG] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is AX |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US472
| [AB SG] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is Cash |  | Len | SG | Jayson
| [AB SG] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is Citi TMP |  | Len | SG | Jayson
| [NB HK] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is VI |  | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK 3 | BEAR , PABLO | US472
| [AB HK] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is DC |  | Len | HK | Jayson
| [NB IN] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is CA |  | Len | IN | Jayson | APAC SYN CORP ¦ APAC SYN IN 3 | BEAR , PABLO | US472
| [AB IN] Verify That Commission Rebate Amount Is Written In Itinerary And Accounting Remarks And FOP Is AX |  | Len | IN | Jayson
| [NB SG] Verify That Merchant Fee Percentage/Amount Not Computed/Written When FOP Is Cash |  | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US267
| [AB SG] Verify That Merchant Fee Percentage/Amount Is Computed/Written When FOP Is VI |  | Len | SG | Jayson
| [AB SG] Verify That Merchant Fee Percentage/Amount Not Computed/Written When FOP Is Citi CTCL |  | Len | SG | Jayson
| [NB HK] Verify That Merchant Fee Percentage/Amount Is Computed/Written When FOP Is VI |  | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK 3 | BEAR , PABLO | US267
| [AB HK] Verify That Merchant Fee Percentage/Amount Is Computed/Written When FOP Is CA |  | Len | HK | Jayson
| [AB HK] Verify That Merchant Fee Percentage/Amount Is Computed/Written When FOP Is TP |  | Len | HK | Jayson
| [NB IN] Verify That Merchant Fee Percentage/Amount Is Computed/Written When FOP Is AX |  | Len | IN | Jayson | APAC SYN CORP ¦ APAC SYN IN 3 | BEAR , PABLO | US267
| [AB IN] Verify That Merchant Fee Percentage/Amount Is Computed/Written When FOP Is DC TMP |  | Len | IN | Jayson
Restrictions | [NB SG] Verify That Default Option Is Pre-Selected And Displayed In The Restrictions Tab | Streamlined | Len | SG | Jayson | APAC SYN CORP ¦ APAC SYN SG | BEAR , SING | US294
| [AB SG] Verify That Default Option Is Pre-Selected And Displayed In The Restrictions Tab | Streamlined | Len | SG | Jayson
| [NB HK] Verify That Default Option Is Pre-Selected And Displayed In The Restrictions Tab | Obsolete | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK | BEAR , SING | US294 | Removed Test Case
| [AB HK] Verify That Default Option Is Pre-Selected And Displayed In The Restrictions Tab | Obsolete | Len | HK | Jayson |  |  |  | Removed Test Case
| [NB IN] Verify That Default Option Is Pre-Selected And Displayed In The Restrictions Tab | Obsolete | Len | IN | Jayson | APAC SYN CORP ¦ APAC SYN IN | BEAR , SING | US294 | Removed Test Case
| [AB IN] Verify That Default Option Is Pre-Selected And Displayed In The Restrictions Tab | Obsolete | Len | IN | Jayson |  |  |  | Removed Test Case

## Client Info
Sub Folder | Test Case | Status | Scripter | Country | Reviewer | Client | Traveller | Tags
Form Of Payment | [NB SG] Verify Airline Is The Merchant Or CWT Is The Merchant Can Be Selected When FOP Is CC | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , SING | US611
| [NB SG] Verify That FOP Line Is Written When FOP Is Cash | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , ARLENE | US324
| [AB SG] Verify That FOP Line Is Written When Manually Entered FOP Is A Diners TMP Card | For Verification | Len | SG
| [NB HK] Verify Airline Is The Merchant Or CWT Is The Merchant Can Be Selected When FOP Is CC | DONE | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US611
| [NB HK] Verify That FOP Line Is Written When FOP Is Cash | Doubts/Clarification | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US324 | Verification on FOP per segment
| [AB HK] Verify That FOP Line Is Written When Manually Entered FOP Is A Diners TMP Card | Doubts/Clarification | Len | HK | Jayson |  |  |  | Verification on FOP per segment
| [NB HK] Verify That FOP Line Is Written When FOP Is Invoice | Doubts/Clarification | Len | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US324
| [AB HK] Verify That FOP Line Is Written When Manually Entered FOP Is A Citi TMP Card | Doubts/Clarification | Len | HK
| [NB IN] Verify That FOP Line is Written When FOP Is Invoice | For Verification | Len | IN |  | APAC SYN CORP ¦ APAC SYN IN | BEAR , INDI | US324
| [AB IN] Verify that FOP line is written when manually entered FOP is a Citi TMP card | For Verification | Len | IN
| [NB HK] Verify that FOP line is written when FOP is credit card (VI) and CWT is The Merchant Is Selected | For Verification | Len | HK | Jayson | APAC SYN CORP ¦ APAC SYN SG | BEAR , HONG | US324 | Data, client is SG
| [NB SG] Verify that FOP Line Is Written When Manually Entered FOP Is AX Card | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , ARLENE | US324
| [NB SG] Verify That FOP Line Is Written When Manually Entered FOP Is VI Card | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US324
| [AB SG] Verify That FOP Line Is Written When Manually Entered FOP Is AX Card | For Verification | Len | SG
[NB OS SG] Verify That Accounting Lines For Other Services Are Written When FOP In The PNR Is Diners TMP and FOP In Other Svcs Panel Is CX

## Delivery
Sub Folder | Test Case | Status | Scripter | Country | Reviewer | Client | Traveller | Tags | Sripter
Email Recipients | [NB IN] Verify That E-Mail Addresses Are Pre-Populated From Both Portrait And GDS Profile For Traveller/Contact | For Verification | Len | IN |  | APAC SYN CORP ¦ APAC SYN IN | BEAR , INDI | US302 | Len
| [AB IN] Verify That E-Mail Addresses Are Pre-Populated From Both Portrait And GDS Profile For Traveller/Contact | For Verification | Len | IN
| [NB HK] Verify That E-Mail Addresses Are Pre-Populated From Both Portrait And GDS Profile For Traveller And Contact | For Verification | Len | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , MHAY | US302 | Len
| [AB HK] Verify That E-Mail Addresses Are Pre-Populated From Both Portrait And GDS Profile For Traveller/Contact | For Verification | Len | HK
| [AB HK] Verify That E-Mail Addresses Are Retrieved From PNR Remarks And Portrait | For Verification | Len | HK
| [NB SG] Verify That E-Mail Addresses Are Pre-Populated From Both Portrait And GDS Profile For Traveller And Contact (Arranger) | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG 4 | BEAR , KMB | US302 | Len
| [AB SG] Verify That E-Mail Addresses Are Pre-Populated From Both Portrait And GDS Profile For Traveller And Contact (Arranger) | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG 4 | BEAR , NAH
On Hold Booking | [NB SG] Verify That Correct Remarks Are Written When Delivery Method Is Non-TKOK And On Hold Reason Is Ticked | For Verification | Len | SG |  | APAC SYN CORP ¦ APAC SYN SG 3 | BEAR , MONT | US711 | Len
| [AB SG] Verify That Correct Remarks Are Written When Delivery Method Is Non-TKOK And No On Hold Reason Is Ticked | For Verification | Len | SG
| [NB HK] Verify That Correct Remarks Are Written When Delivery Method Is TKOK and On Hold Reason Is Ticked | For Verification | Len | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US711 | Len
| [AB HK] Verify That Correct Remarks Are Written When Delivery Method Is TKOK And No On Hold Reason Is Ticked | For Verification | Len | HK
| [NB IN] Verify That Correct Remarks Are Written When Delivery Method Is Non-TKOK And On Hold Reason Is Ticked | For Verification | Len | IN |  | APAC SYN CORP ¦ APAC SYN IN 3 | BEAR , NIYAK | US711 | Len
| [AB IN] Verify That Correct Remarks Are Written When Delivery Method Is Non-TKOK And No On Hold Reason Is Ticked | For Verification | Len | IN
| [NB SG] Verify That Ticketing Element Is Written When Delivery Method Is TK TL (Auto Ticket) With No On Hold Selected | For Verification | Len | SG |  | APAC SYN CORP ¦ AUTOMATION SG - US304 | BEAR , SGTHREEZEROFOUR | US304 | Len
| [AB SG] Verify That Ticketing Element Is Written When Delivery Method Is TK TL (Auto Ticket) With No On Hold Selected | For Verification | Len | SG
| [NB HK] Verify That Ticketing Element Is Written When Delivery Method Is TK XL (Auto Cancel) With No On Hold Selected | Doubts/Clarification | Len | HK |  | APAC SYN CORP ¦ AUTOMATION HK - US304 | BEAR , HKTHREEZEROFOUR | US304 | Len
| [AB HK] Verify That Ticketing Element Is Written When Delivery Method Is TK OK (No Queue Placement) With Multiple On Hold Selected | Doubts/Clarification | Len | HK
| [NB IN] Verify That Ticketing Element Is Written When Delivery Method Is TK OK (No Queue Placement) With Multiple On Hold Selected | For Verification | Len | IN |  | APAC SYN CORP ¦ AUTOMATION IN - US304 | BEAR , INTHREEZEROFOUR | US304 | Len
| [AB IN] Verify That Ticketing Element Is Written When Delivery Method Is TK XL (Auto Cancel) With Single On Hold Selected | For Verification | Len | IN
| [AB IN] Verify That Ticketing Element Is Written When Delivery Method Is TK TL (Auto Ticket) With Multiple On Hold Selected | For Verification | Len | IN
| [NB HK] Verify That PNR Is Queued In Aqua When Follow Up Date Is Set To Future Date And Awaiting Itinerary Segment Is Selected | For Verification | Len | HK |  | APAC SYN CORP ¦ AUTOMATION HK - US710 | BEAR , HKSEVENONEZERO | US710 | Len
| [AB HK] Verify That PNR Is Queued In Aqua When Follow Up Date Is Set Today And Awaiting Customer References Is Selected | For Verification | Len | HK
| [AB HK] Verify That PNR Is Queued In Aqua When No Onhold Is Selected | For Verification | Len | HK
| [IN NB] Verify That PNR Is Queued In Aqua When Follow Up Date Is Set Today And Awaiting Approval Is Selected | For Verification | Len | IN |  | APAC SYN CORP ¦ AUTOMATION IN - US710 | BEAR , INSEVENONEZERO | US710 | Len
| [IN AB] Verify That PNR Is Queued In Aqua When Follow Up Date Is Set To Today And Multiple OnHold Is Selected | For Verification | Len | IN
| [NB SG] Verify That PNR Is Queued In Aqua When Follow Up Date Is Set Today And No Onhold Selected | For Verification | Len | SG |  | APAC SYN CORP ¦ AUTOMATION SG - US710 | BEAR , SGSEVENONEZERO | US710 | Len
| [AB SG] Verify That PNR Is Queued In Aqua When Follow Up Date Is Set To Future Date And Awaiting Secure Flight Data Is Selected | For Verification | Len | SG
Ticketing Follow Updates | [NB HK] Verify That Warning Is Displayed If Follow Up Date is Local Holiday | For Review | Ankit Tomar | HK |  | APAC SYN CORP ¦ AUTOMATION HK - US587 | BEAR , HKFIVEEIGHTSEVEN | US587 | Ankith Tomar
| [AB HK] Verify That Warning Is Displayed If Follow Up Date is Local Holiday | Not Started |  | HK
| [NB IN] Verify That Warning Is Displayed If Ticketing Date And Follow Up Date is Local Holiday | For Review | Ankit Tomar | IN |  | APAC SYN CORP ¦ AUTOMATION IN - US587 | BEAR , INFIVEEIGHTSEVEN | US587 | Ankith Tomar
| [AB IN] Verify That Warning Is Displayed If Ticketing Date And Follow Up Date is Local Holiday | Not Started |  | IN
| [NB SG] Verify That Warning Is Displayed If Ticketing Date is Local Holiday | For Review | Ankit Tomar | SG |  | APAC SYN CORP ¦ AUTOMATION SG - US587 | BEAR , SGFIVEEIGHTSEVEN | US587 | Ankith Tomar
| [AB SG] Verify That Warning Is Displayed If Ticketing Date is Local Holiday |  |  | SG

## Other Services
Sub Folder | Test Case | Status | Scripter | Country | Reviewer | Client | Traveller | Tags
Remarks | [SG NB] Verify That Exchange Order Remarks And Itinerary Remarks Fields Are Working Correctly | For Review | Gajendra | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , LEN | US720 , US453
| [SG NB] Verify That Selected Itinerary Remarks Are Written In The PNR In The Correct Order | For Review | Gajendra | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , LEN | US720 , US453
| [SG AB] Verify That Selected Itinerary Remarks Are Written In The PNR In The Correct Order | Not Started |  | SG |  |  |  | US720 , US453
| [SG OS] Verify That On Finish PNR Selected Itinerary Remarks Are Written In The PNR In The Correct Order | Not Started |  | SG |  |  |  | US720 , US453
| [SG OS] Verify That On Retrieval Of PNR Selected Itinerary Remarks Are Written In The PNR In The Correct Order | Not Started |  | SG |  |  |  | US720 , US453
| [HK NB] Verify That Selected Itinerary Remarks Are Written In The PNR In The Correct Order | For Review | Gajendra | HK |  | APAC SYN CORP ¦ AUTOMATION HK - OS REMARK TAB (US863) | BEAR , EIGHTSIXTHREE | US720 , US453
| [HK AB] Verify That Selected Itinerary Remarks Are Written In The PNR In The Correct Order | Not Started |  | HK
| [SG NB] Verify That Itinerary And Exchange Order Can Be Entered Manually And Written In The PNR | Not Started |  | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , LEN | US720 , US453 , US863
| [SG AB][OS] Verify That Itinerary And Exchange Order Can Be Entered Manually And Written In The PNR | Not Started |  | SG
| [SG OS] Verify That Itinerary And Exchange Order Can Be Entered Manually And Written In The PNR | Not Started |  | SG
| [HK NB][OS] Verify That Itinerary And Exchange Order Can Be Entered Manually And Written In The PNR | Not Started |  | HK |  | APAC SYN CORP ¦ AUTOMATION HK - OS REMARK TAB (US863) | BEAR , EIGHTSIXTHREE | US863
| [HK AB][OS] Verify That Itinerary And Exchange Order Can Be Entered Manually And Written In The PNR | Not Started |  | HK |  |  |  | US863
| [HK OS] Verify That Itinerary And Exchange Order Can Be Entered Manually And Written In The PNR | Not Started |  | HK
Service Info | [SG NB] Verify That Other Services With GST Fields Are Displayed In Service Info Tab | Doubts/Clarification | Sharad | SG |  | APAC SYN CORP ¦ APAC SG OS AUTOMATION | BEAR , SGOTHERS | US686 , US624 , US668
| [SG AB] Verify That Other Services Without GST Fields Are Displayed In Service Info Tab | Not Started |  | SG |  |  |  | US686 , US624
| [SG OS] Verify That Other Services Without GST Fields Are Displayed In Service Info Tab | Not Started |  | SG |  |  |  | US686 , US624
| [HK NB] Verify That Other Services Without GST Fields Are Displayed In Service Info Tab | Not Started |  | HK |  | APAC SYN CORP ¦ APAC HK OS AUTOMATION | BEAR , HKOTHERS | US686 , US624
| [HK AB] Verify That Other Services Without GST Fields Are Displayed In Service Info Tab | Not Started |  | HK
| [HK OS] Verify That Other Services Without GST Fields Are Displayed In Service Info Tab | Not Started |  | HK
| [SG NB] Verify That Accounting Lines For Other Services With GST Are Written When FOP Is Cash or Invoice And BTA Description Is Not Blank | In Progress | Mahonath | SG |  | APAC SYN CORP ¦ APAC SG OS AUTOMATION | BEAR , SGOTHERS | US456 , US723 , NOT_READY
| [SG AB] Verify That Accounting Lines For Other Services With GST Are Written When FOP Is Cash or Invoice And BTA Description Is Blank | Not Started |  | SG |  |  |  | US456 , US723 , NOT_READY
| [SG OS] Verify That Accounting Lines For Other Services With GST Are Written When FOP Is Credit Card (CC) And BTA Description Is Not Blank | Not Started |  | SG |  |  |  | US456 , US723 , NOT_READY
| [SG OS] Verify That Accounting Lines For Other Services With GST Are Written When FOP Is Credit Card (CC) And BTA Description Is Blank | Not Started |  | SG |  |  |  | US456 , US723 , NOT_READY
| [SG OS] Verify That Accounting Lines For Other Services With GST Are Written When FOP Is Credit Card (CX) And BTA Description Is Not Blank | Not Started |  | SG |  |  |  | US456 , US723 , NOT_READY
| [SG OS] Verify That Accounting Lines For Other Services With GST Are Written When FOP Is Credit Card (CX) And BTA Description Is Blank | Not Started |  | SG |  |  |  | US456 , US723 , NOT_READY
| [SG NB] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Cash or Invoice And BTA Description Is Not Blank | Not Started |  | SG |  | APAC SYN CORP ¦ APAC SG OS AUTOMATION | BEAR , SGOTHERS | US457 , US724
| [SG AB] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Cash or Invoice And BTA Description Is Blank | Not Started |  | SG |  |  |  | US457 , US724
| [SG OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CC) And BTA Description Is Not Blank | Not Started |  | SG |  |  |  | US457 , US724
| [SG OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CC) And BTA Description Is Blank | Not Started |  | SG |  |  |  | US457 , US724
| [SG OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CX) And BTA Description Is Not Blank | Not Started |  | SG |  |  |  | US457 , US724
| [SG OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CX) And BTA Description Is Blank | Not Started |  | SG |  |  |  | US457 , US724 , Not_Ready
| [HK NB] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Cash or Invoice And BTA Description Is Not Blank | Not Started |  | HK |  | APAC SYN CORP ¦ APAC HK OS AUTOMATION | BEAR , HKOTHERS | US457 , US724
| [HK AB] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Cash or Invoice And BTA Description Is Blank | Not Started |  | HK |  |  |  | US457 , US724
| [HK OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CC) And BTA Description Is Not Blank | Not Started |  | HK |  |  |  | US457 , US724
| [HK OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CC) And BTA Description Is Blank | Not Started |  | HK |  |  |  | US457 , US724
| [HK OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CX) And BTA Description Is Not Blank | Not Started |  | HK |  |  |  | US457 , US724
| [HK OS] Verify That Accounting Lines For Other Services Without GST Are Written When FOP Is Credit Card (CX) And BTA Description Blank | Not Started |  | HK |  |  |  | US457 , US724 , Not_Ready
| [IN NB] Verify That Correct Remarks Will Be Written Using Amount FOP Type is Cash or Invoice | Not Started |  | IN |  | APAC SYN CORP ¦ APAC SYN IN | BEAR , SING | NOT_READY
| [IN AB] Verify That Correct Remarks Will Be Written Using Amount FOP Type is CX | Not Started |  | IN |  |  |  | NOT_READY
| [IN NB] Verify That Correct Remarks Will Be Written Using Percentage FOP Type is BTC. | Not Started |  | IN |  |  |  | NOT_READY
| [IN AB] Verify That Correct Remarks Will Be Written Using Percentage FOP Type is CC | Not Started |  | IN |  |  |  | NOT_READY
| [SG NB OS] Verify That Accounting Lines For Other Services Is Written With CX2 Fee Code When Credit Card Type Is AX | Not Started |  | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , ARIS | US857, NOT_READY , EXPECTED_TO_FAIL
| [SG AB OS] Verify That Accounting Lines For Other Services Is Written With CX3 Fee Code When Credit Card Type Is DC | Not Started |  | SG |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [SG OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is VI | Not Started |  | SG |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [SG OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is CA | Not Started |  | SG |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [SG OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is MC | Not Started |  | SG |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [SG OS] Verify That Accounting Lines For Other Services Is Written With CX5 Fee Code When Credit Card Type Is TP | Not Started |  | SG |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [SG OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is JC | Not Started |  | SG |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK NB OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is VI | Not Started |  | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK AB OS] Verify That Accounting Lines For Other Services Is Written With CX5 Fee Code When Credit Card Type Is TP | Not Started |  | HK |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK OS] Verify That Accounting Lines For Other Services Is Written With CX2 Fee Code When Credit Card Type Is AX | Not Started |  | HK |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is MC | Not Started |  | HK |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK OS] Verify That Accounting Lines For Other Services Is Written With CX3 Fee Code When Credit Card Type Is DC | Not Started |  | HK |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is CA | Not Started |  | HK |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [HK OS] Verify That Accounting Lines For Other Services Is Written With CX4 Fee Code When Credit Card Type Is JC | Not Started |  | HK |  |  |  | US857, NOT_READY , EXPECTED_TO_FAIL
| [NB OS SG] Verify That Service Info Fields Of Insurance Behave Correctly And Written In The PNR When FOP Is CC | Not Started |  | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , DOS | US462 , NOT_READY
| [AB OS SG] Verify That Service Info Fields Of Insurance Behave Correctly And Written In The PNR When FOP Is CX | Not Started |  | SG |  |  |  | US462 , NOT_READY
| [OS SG] Verify That Service Info Fields Of Insurance Behave Correctly And Written In The PNR When FOP Is Cash or Invoice | Not Started |  | SG |  |  |  | US462 , NOT_READY
| [NB OS HK] Verify That Service Info Fields Of Insurance Behave Correctly And Written In The PNR When FOP Is CC | Not Started |  | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US500 , NOT_READY
| [AB OS HK] Verify That Service Info Fields Of Insurance Behave Correctly And Written In The PNR When FOP Is CX | Not Started |  | HK |  |  |  | US500 , NOT_READY
| [OS HK] Verify That Service Info Fields Of Insurance Behave Correctly And Written In The PNR When FOP Is Cash or Invoice | Not Started |  | HK |  |  |  | US500 , NOT_READY
Vendor Info | [SG][NB] Verify That Vendor Information Fields Are Displayed In Vendor Info Tab | Not Started |  | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , SING | US480
| [SG][AB] Verify That Vendor Information Fields Are Displayed In Vendor Info Tab | Not Started |  | SG |  |  |  | US480
| [HK][NB] Verify That Vendor Information Fields Are Displayed In Vendor Info Tab | Not Started |  | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US480
| [HK][AB] Verify That Vendor Information Fields Are Displayed In Vendor Info Tab | Not Started |  | HK |  |  |  | US480
Visa Info | [HK NB OS] Verify That Visa Processing Behaves Correctly And Written In The PNR When FOP Is CX | Doubts/Clarification | Harsha | HK |  | APAC SYN CORP ¦ APAC SYN HK | BEAR , HONG | US463
| [HK AB OS] Verify That Visa Processing Behaves Correctly And Written In The PNR When FOP Is CC | Not Started |  | HK |  |  |  | US463
| [HK OS] Verify That Visa Processing Behaves Correctly And Written In The PNR When FOP Is Invoice | Not Started |  | HK |  |  |  | US463
| [SG][NB][OS] Verify That Visa Cost Fields Behave Correctly In Other Services Panel And Written In The PNR When FOP Is CC | Doubts/Clarification | Harsha | SG |  | XYZ Company PV2 ¦ HK Automation US465 | BEAR , SGFOURSIXFIVE | US465 , NOT_READY
| [SG][AB][OS] Verify That Visa Cost Fields Behave Correctly In Other Services Panel And Written In The PNR When FOP Is CX | Not Started |  | SG |  |  |  | US465 , NOT_READY
| [SG][OS] Verify That Visa Cost Fields Behave Correctly In Other Services Panel And Written In The PNR When FOP Is Cash Or Invoice | Not Started |  | SG |  |  |  | US465 , NOT_READY
| [NB OS SG] Verify That Visa Handling Behave Correctly In Other Services Panel And Written In The PNR When FOP Type Is CX | Doubts/Clarification | Harsha | SG |  | APAC SYN CORP ¦ APAC SYN SG | BEAR , DOS | US466 , NOT_READY
| [AB OS SG] Verify That Visa Handling Behave Correctly In Other Services Panel And Written In The PNR When FOP Type Is CX | Not Started |  | SG |  |  |  | US466 , NOT_READY
| [OS SG] Verify That Visa Handling Behave Correctly In Other Services Panel And Written In The PNR When FOP Type Is Cash Or Invoice | Not Started |  | SG |  |  |  | US466 , NOT_READY

## Pspt And Visa
Sub Folder | Test Case | Status | Scripter | Country | Reviewer | Client | Traveller | Tags
| [NB IN] Verify That For International Trip, Destination And Transit Countries Are Written In Passport & Visa Info Tab And PNR | DONE | Jayson | IN |  | APAC SYN CORP ¦ AUTOMATION HK - US555 | BEAR, HKFIVEFIVEFIVE | US810
| [AB IN] Verify That For International Trip, Destination And Transit Countries Are Written In Passport & Visa Info Tab And PNR | DONE | Jayson | IN |  |  |  | US810
| [NB SG] Verify That For International Trip, Destination And Transit Countries Are Written In Passport & Visa Info Tab And PNR | DONE | Jayson | SG |  | APAC SYN CORP ¦ AUTOMATION HK - US555 | BEAR, HKFIVEFIVEFIVE | US810
| [AB SG] Verify That For International Trip, Destination And Transit Countries Are Written In Passport & Visa Info Tab And PNR | DONE | Jayson | SG |  |  |  | US810
| [NB HK] Verify That For International Trip, Destination And Transit Countries Are Written In Passport & Visa Info Tab And PNR | DONE | Jayson | HK |  | APAC SYN CORP ¦ AUTOMATION HK - US555 | BEAR, HKFIVEFIVEFIVE | US810
| [AB HK] Verify That For International Trip, Destination And Transit Countries Are Written In Passport & Visa Info Tab And PNR | DONE | Jayson | HK |  |  |  | US810

## Workflow
Sub Folder | Test Case | Status | Scripter | Country | Reviewer | Client | Traveller | Tags
Workflow | [NB HK] Verify That Update PNR Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | HK |  |  |  | us765, not_ready, for_removal
| [AB HK] Verify That Update PNR Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | HK |  |  |  | us765, not_ready, for_removal
| [NB HK] Verify That Create Shell Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | HK |  |  |  | us765, not_ready, for_removal
| [NB IN] Verify That Update PNR Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | IN |  |  |  | us765, not_ready, for_removal
| [AB IN] Verify That Update PNR Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | IN |  |  |  | us765, not_ready, for_removal
| [NB IN] Verify That Create Shell Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | IN |  |  |  | us765, not_ready, for_removal
| [NB SG] Verify That Update PNR Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | SG |  |  |  | us765, not_ready, for_removal
| [AB SG] Verify That Update PNR Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | SG |  |  |  | us765, not_ready, for_removal
| [NB SG] Verify That Create Shell Workflow Panel And Correct Ordering Of Workflow Panels Are Displayed | Streamlined | Jayson | SG |  |  |  | us765, not_ready, for_removal