## Plan
Date | Day | Suni | Happy | Chuckie | Marge | Shila | Jayson | Wins | Kitz | Dos | Release |  | Suni
2016-11-14 | Monday | 6 | 7 | 7 | 6 | 4 | Training | 6 | 6 | Training | 12 | 2 | 30 | 4.2857 |  |  |  | Critical | High | Medium | Effort | Total
2016-11-15 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 18 | 3 | 30 | 4.2857 |  |  | Done - V3 F.W. | 0 | 0 | 0 | - | -
2016-11-16 | Wednesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 12 | 2 | 30 | 4.2857 |  |  | Done - V2 F.W. | 196 | 0 | 0 | 5 | 980
2016-11-17 | Thursday | 6 | 7 | 7 | 6 | 4 | VL | 6 | 6 | 6 | 18 | 3 | 30 | 4.2857 |  |  | Migrate Done V2. FW | 26 | 0 | 0 | 7 | 182
2016-11-18 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 18 | 3 | 30 | 4.2857 |  |  | In Progress | 4 | 0 | 0 | 7 | 28
2016-11-21 | Monday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 18 | 3 | 30 | 4.2857 |  |  | Not Started | 32 | 0 | 0 | 7 | 224
2016-11-22 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 18 | 3 | 30 | 4.2857 |  |  | Obsolete | 15 | 0 | 0 | 9.75 | 146.25
2016-11-23 | Wednesday | VL | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 18 | 3 | 24 | 3.4286 |  |  | No Existing | 19 | 0 | 0 | 9.75 | 185.25
2016-11-24 | Thursday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 12 | 2 | 30 | 4.2857 |  |  |  | 292 | 0 | 0 |  | 1745.5
2016-11-25 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 12 | 2 | 30 | 4.2857
2016-11-28 | Monday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 12 | 2 | 30 | 4.2857 |  |  |  | Critical | High | Medium | Total
2016-11-29 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | VL | 6 | 6 | 12 | 2 | 30 | 4.2857 |  |  | Effort | 1234.5 | 0 | 0 | 1234.5
2016-11-30 | Wednesday | HL | HL | HL | HL | HL | HL | HL | HL | HL | 0 | 0 | 0 | 0 |  |  | End Date | 2016-12-16 | - | -
2016-12-01 | Thursday | 6 | 7 | 7 | 6 | 4 | VL | 6 | 6 | 6 | 18 | 3 | 30 | 4.2857 |  |  | Capacity | 1248 | 0 | 0 | 1248
2016-12-02 | Friday | 6 | 7 | VL | 6 | 4 | VL | 6 | 6 | 6 | 18 | 3 | 23 | 3.2857 |  |  | Variance | 13.5 | 0 | 0 | 13.5
2016-12-05 | Monday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-06 | Tuesday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 0 | 15 | 2.5 | 30 | 4.2857
2016-12-07 | Wednesday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-08 | Thursday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-09 | Friday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857 |  |  |  |  | 7.224
2016-12-12 | Monday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | VL | 15 | 2.5 | 30 | 4.2857 |  |  |  |  | 28.8958
2016-12-13 | Tuesday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-14 | Wednesday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-15 | Thursday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-16 | Friday | 6 | 7 | 7 | 6 | 4 | 3 | 6 | 6 | 6 | 21 | 3.5 | 30 | 4.2857
2016-12-19 | Monday | 6 | 7 | 6 | VL | 4 | 3 | VL | VL | VL | 3 | 0.5 | 23 | 3.2857
2016-12-20 | Tuesday | 6 | 7 | 6 | VL | 4 | 3 | VL | VL | VL | 3 | 0.5 | 23 | 3.2857
2016-12-21 | Wednesday | 6 | VL | 6 | VL | 4 | 3 | VL | VL | VL | 3 | 0.5 | 16 | 2.2857
2016-12-22 | Thursday | 3 | 7 | 6 | VL | 4 | 3 | VL | VL | VL | 3 | 0.5 | 20 | 2.8571
2016-12-23 | Friday | VL | VL | VL | VL | VL | VL | VL | VL | VL | 0 | 0 | 0 | 0
2016-12-26 | Monday | HL | HL | HL | HL | HL | HL | HL | HL | HL | 0 | 0 | 0 | 0
2016-12-27 | Tuesday | 6 | 7 | 6 | VL | VL | VL | VL | VL | VL | 0 | 0 | 19 | 2.7143
2016-12-28 | Wednesday | 6 | 7 | 6 | VL | 4 | VL | VL | VL | VL | 0 | 0 | 23 | 3.2857
2016-12-29 | Thursday | 6 | VL | 6 | VL | 4 | VL | VL | VL | VL | 0 | 0 | 16 | 2.2857
2016-12-30 | Friday | HL | HL | HL | HL | HL | HL | HL | HL | HL | 0 | 0 | 0 | 0
2016-01-02 | Monday | HL | HL | HL | HL | HL | HL | HL | HL | HL | 0 | 0 | 0 | 0
2016-01-03 | Tuesday | 6 | 7 | 7 | VL | 7 | VL | 6 | VL | VL | 6 | 1 | 27 | 3.8571
2016-01-04 | Wednesday | 6 | 7 | 7 | VL | 7 | 3 | 6 | VL | 6 | 15 | 2 | 27 | 3.8571
2016-01-05 | Thursday | 6 | Training | 7 | VL | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-01-06 | Friday | 6 | Training | 7 | VL | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-01-09 | Monday | 6 | Training | 7 | 6 | Training | Training | 2 | 2 | 2 | 6 | 2 | 19 | 2.7143
2016-01-10 | Tuesday | 6 | Training | 7 | 6 | Training | Training | 2 | 2 | 2 | 6 | 2 | 19 | 2.7143
2016-01-11 | Wednesday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-12 | Thursday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-13 | Friday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-16 | Monday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-17 | Tuesday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-18 | Wednesday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-19 | Thursday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-20 | Friday | 6 | Training | 7 | 6 | Training | 3 | 2 | 2 | 2 | 9 | 1.2857 | 19 | 2.7143
2016-01-23 | Monday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-01-24 | Tuesday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-01-25 | Wednesday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-01-26 | Thursday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-01-27 | Friday | 6 | VL | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-01-30 | Monday | VL | VL | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-01-31 | Tuesday | VL | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-02-01 | Wednesday | VL | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-02-02 | Thursday | VL | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-02-03 | Friday | VL | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 13 | 1.8571
2016-02-06 | Monday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | VL | 15 | 2.1429 | 19 | 2.7143
2016-02-07 | Tuesday | 6 | Training | VL | 6 | Training | 3 | 6 | 6 | VL | 15 | 2.1429 | 12 | 1.7143
2016-02-08 | Wednesday | 6 | Training | VL | 6 | Training | 3 | 6 | 6 | VL | 15 | 2.1429 | 12 | 1.7143
2016-02-09 | Thursday | 6 | Training | VL | 6 | Training | 3 | 6 | 6 | VL | 15 | 2.1429 | 12 | 1.7143
2016-02-10 | Friday | 6 | Training | VL | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 12 | 1.7143
2016-02-13 | Monday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-14 | Tuesday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-15 | Wednesday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-16 | Thursday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-17 | Friday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-20 | Monday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-21 | Tuesday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-22 | Wednesday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-23 | Thursday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
2016-02-24 | Friday | 6 | Training | 7 | 6 | Training | 3 | 6 | 6 | 6 | 21 | 3 | 19 | 2.7143
Release Qas
Migration to V3 and Review of Suni's Team Output
| 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2016-01-16 | 2017-01-23 | 2017-01-30 | 2016-02-06 | 2016-02-13 | 2016-02-20
1 | Grouping | 4 | 2 | 3 | 3 | 0.5 | 0 | 0 | 2 | 1 | 3 | 3 | 2 | 3 | 3
2 | 3 | 4 | 2 | 3 | 4 | 0.5 | 0 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 3
3 | 3 | 4 | Holiday | 3 | 3 | 0.5 | 0 | 2 | 1 | 1 | 3 | 3 | 2 | 3 | 3
4 | 4 | 3 | 3 | 4 | 3 | 0.5 | 0 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 3
5 | 4 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 1 | 2 | 3 | 3 | 3 | 3 | 3
TOTAL | 14 | 18 | 10 | 16 | 15 | 2 | 0 | 9 | 7 | 6 | 15 | 15 | 11 | 15 | 15 | 0
Suni's Team
Migration to V3 + DS
| 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2016-01-16 | 2017-01-23 | 2017-01-30 | 2016-02-06 | 2016-02-13 | 2016-02-20
1 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 2 | 2 | 2 | 1 | 2 | 2 | 2
2 | 4 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1.7143 | 3 | 3
3 | 4 | 3 | Holiday | 4 | 4 | 3 | 3 | 4 | 2 | 2 | 2 | 1 | 1.7143 | 2 | 2
4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 3 | 3 | 3 | 2 | 1.7143 | 3 | 3
5 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1.7143 | 2 | 2
TOTAL | 20 | 20 | 16 | 20 | 20 | 12 | 8 | 10 | 12 | 12 | 12 | 7 | 8.8571 | 12 | 12 | 177.8571
177.8571
Total for both teams | 34 | 38 | 26 | 36 | 35 | 14 | 8 | 19 | 19 | 18 | 27 | 22 | 19.8571 | 27 | 27
Target % | 11.22% | 23.76% | 32.34% | 44.22% | 55.78% | 60.4% | 63.04% | 69.31% | 75.58% | 81.52% | 90.43% | 97.69% | 104.2% | 113.2% | 122.1%
Actual | 30 | 40 | 26 | 35 | 19 | 10 | 10 | 12 | 18 | 21 | 19 | 9 | 10
Streamlined/Obsolete/Not for Automation | 0 | 0 | 26 | 0 | 0 | 1 | 0 | 2 | 6 | 4 | 3 | 0 | 1
| 9.901% | 23.1% | 40.26% | 51.82% | 58.09% | 61.72% | 65.02% | 69.64% | 77.56% | 85.81% | 93.07% | 96.04% | 99.67%
3
Total TCs | 303 | [15 empty] | 3
3
3
3
3
3
3
3
3
Note on O1: Gaviola, Pam: 5 hours for migrating to V3 framework + 1 hour to review Suni's team's output
Note on B92: Gaviola, Pam: 7.25 hours per TC because review will be done by Wins, Kitz, Dos and Brent

## Actual
Date | Day | Suni | Happy | Chuckie | Marge | Shila | Jayson | Wins | Kitz | Dos | Brent | Dhel | Karren | Nikki | Gryz | Chin | Pleng | Ryan | Jed | JP |  |  | Wins, Kitz, Dos, Brent | Release QAs | Total TCs for Release Qas
2016-11-14 | Monday | SL | SL | 7 | 6 | 4 | Training | 6 | 6 | Training | 6 | [9 empty] | 18 |  | 0 | 0 | 0 |  | Critical | High | Medium | Effort | Total
2016-11-15 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | [9 empty] | 24 |  | 4 | 0 | 4 | Done - V3 F.W. | 0 | 0 | 0 | - | -
2016-11-16 | Wednesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 6 | [9 empty] | 18 |  | 3 | 0 | 3 | Done - V2 F.W. | 196 | 0 | 0 | 5 | 980
2016-11-17 | Thursday | 6 | 7 | 7 | 6 | 4 | VL | 6 | 6 | 6 | 6 | [9 empty] | 24 |  | 4 | 0 | 4 | Migrate Done V2. FW | 26 | 0 | 0 | 7 | 182
2016-11-18 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | SL | 6 | [9 empty] | 18 |  | 3 | 0 | 3 | In Progress | 4 | 0 | 0 | 7 | 28
2016-11-21 | Monday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | [9 empty] | 24 |  | 4 | 0 | 4 | Not Started | 32 | 0 | 0 | 7 | 224
2016-11-22 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | [9 empty] | 24 |  | 4 | 0 | 4 | Obsolete | 15 | 0 | 0 | 9.75 | 146.25
2016-11-23 | Wednesday | VL | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | [9 empty] | 24 |  | 4 | 0 | 4 | No Existing | 19 | 0 | 0 | 9.75 | 185.25
2016-11-24 | Thursday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 6 | [9 empty] | 18 |  | 3 | 0 | 3 |  | 292 | 0 | 0 |  | 1745.5
2016-11-25 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 6 | [9 empty] | 18 |  | 3 | 0 | 3
2016-11-28 | Monday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | VL | 6 | 6 | 6 | 6 | VL | 6 | 6 | 6 | 6 | 6 | 6 | 48 | 10.8 | 3 | 10 | 13 |  | Critical | High | Medium | Total
2016-11-29 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | VL | 6 | 6 | 6 | 6 | 6 | 6 | 48 | 10.8 | 4 | 11 | 15 | Effort | 1234.5 | 0 | 0 | 1234.5
2016-11-30 | Wednesday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | 0 | 0 | 0 | 0 | 0 | End Date | 2016-12-16 | - | -
2016-12-01 | Thursday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | VL | VL | 6 | 6 | 6 | 6 | 6 | 42 | 10.8 | 4 | 11 | 15 | Capacity | 1248 | 0 | 0 | 1248
2016-12-02 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | VL | 6 | VL | VL | 6 | 6 | 6 | 6 | 6 | 36 | 10.8 | 4 | 11 | 15 | Variance | 13.5 | 0 | 0 | 13.5
2016-12-05 | Monday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | VL | 6 | 6 | VL | 6 | 6 | 6 | VL | VL | 30 | 10.8 | 4 | 11 | 15
2016-12-06 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | VL | 6 | 6 | VL | 6 | 6 | 6 | 6 | 6 | 42 | 10.8 | 4 | 10 | 14
2016-12-07 | Wednesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 54 | 10.8 | 4 | 11 | 15
2016-12-08 | Thursday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | VL | 6 | 6 | 6 | 6 | 48 | 10.8 | 4 | 11 | 15
2016-12-09 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | VL | 6 | 6 | 6 | 6 | 48 | 10.8 | 4 | 11 | 15 |  |  | 7.224
2016-12-12 | Monday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | VL | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | VL | 6 | 48 | 10.8 | 3 | 11 | 14 |  |  | 28.8958
2016-12-13 | Tuesday | 6 | 7 | 7 | 6 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 54 | 10.8 | 4 | 10 | 14
2016-12-14 | Wednesday | 6 | 7 | 7 | 6 | 4 | 0 | VL | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 54 | 10.8 | 3 | 11 | 14
2016-12-15 | Thursday | 6 | 7 | 7 | 6 | 4 | 0 | VL | 6 | VL | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 54 | 10.8 | 2 | 11 | 13
2016-12-16 | Friday | 6 | 7 | 7 | 6 | 4 | 0 | VL | 6 | VL | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 54 | 10.8 | 2 | 11 | 13
2016-12-19 | Monday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | 1830
2016-12-20 | Tuesday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-21 | Wednesday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-22 | Thursday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-23 | Friday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-26 | Monday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-27 | Tuesday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-28 | Wednesday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-29 | Thursday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
2016-12-30 | Friday | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL | HL
Release Qas
Migration to V3 and Review of Suni's Team Output
| 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12
1 | Grouping | 4 | 13 | 15 | 14
2 | 3 | 4 | 15 | 14 | 14
3 | 3 | 4 | Holiday | 15 | 14
4 | 4 | 3 | 15 | 15 | 13
5 | 4 | 3 | 15 | 15 | 13 | 232
TOTAL | 14 | 18 | 58 | 74 | 68
Suni's Team
Migration to V3 + DS
| 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12
1 | 4 | 4 | 4 | 4 | 4
2 | 4 | 5 | 4 | 4 | 5
3 | 4 | 3 | Holiday | 4 | 4
4 | 4 | 4 | 4 | 4 | 4
5 | 4 | 4 | 5 | 4 | 4 | 98
TOTAL | 20 | 20 | 17 | 20 | 21
| 34 | 38 | 75 | 94 | 89 | 330
Actual | 30
Note on X1: Gaviola, Pam: 5 hours for migrating to V3 framework + 1 hour to review Suni's team's output
Note on B52: Gaviola, Pam: 7.25 hours per TC because review will be done by Wins, Kitz, Dos and Brent

## Activities
Activities | # of TCs | Hours | Owner | Remarks | Assigned Qas | Duration in days | Daily Output | 14-Nov | 21-Nov | 28-Nov | 5-Dec | 12-Dec
Grouping | 292 | 24 | Release QAs |  | 4 | 1
Migration to V3 + DS | 97 | 692.75 | Suni |  | 4.5 | 25.6574 | 3.7806
Review | 97 | 72.75 | Release QAs |  | 1 |  | 1.3333
Migration to V3 + Review | 196 | 980 | Release QAs |  | 13 | 23 | 8.5217
Nightly Runs |  |  | Suni
22.5

## Notes
Definition of Done
Part of nightly run
data setup
new framework
reviewed

## Diary
2016-11-14 | Suni and Happy on sick leave
2016-11-18 | Dos on sick leave; Suni's laptop broke down
2016-11-23 | Jayson on sick leave
2016-11-24 | Jayson on training
2016-11-25 | Wins on half day sick leave; Chuckie on whole day sick leave; Jayson on training
2016-12-02 | Portrait down whole day
2016-12-14 | Happy on SL; Shila half day
2016-12-27 | Happy on SL
2017-01-04 | Happy on Half day leave; Shila on SL
2017-01-17 | Marge on half day SL
2017-01-24 | Winston on half day SL